## Protocol for CT Steps
Set-Up Steps | Date Task Completed | Responses-Notes
Ticket Created by SH – Proposed Cost | 2024-10-10
Create the CT Template Outlining Old Site with New Site | 2024-10-14
Count Pages, Images, Links, Contacts, Conversions, FAQ, Videos, Calendar of Events, Locations from Old Site to New Site and put into CT Template | 2024-10-14
Send SH the Counted Items to send actual invoice estimate
Set up the estimated completion time and send SH
Send the Client an Email (#1) advising we are starting and send them a note that we will create the old layout and new layout and send them an approval email | 2024-10-14
Set up the lay-out of the old site and confirm all counts | 2024-10-15
Save the CT outline-layout of the old site to the Ticket | 2024-10-14
Set up the old layout (Columns A/B) and figure out how that translate to the new site (where do we propose to put this information) *Save to Ticket in Excel Spreadsheet* | 2024-10-15
Send the Client an Email (#2) with the template for the old to new and request approval but moving on if they do not approve/Compare information in template | 2024-10-15
Download Images into My Image Album and set up individual albums | 2024-10-15
Download Documents (Convert Word to PDF and download the others to Document folders) and set up individual folders | 2024-10-15
After outline of content confirmed, begin dragging and dropping pages around and set within tabs and pages | 2024-10-17
Copy and Paste verbiage, content, images and documents onto each page **Make note of transferred information to new site columns on CT template** | 2024-10-22
Email from ticket any day you need information from account | 2024-10-22
Make notes of your daily progress in the Resolution Section of the website with date/initials/general outline of what you transferred | 2024-10-22
After transfer complete, ask colleague to check your work
Send Final Email(#3) to client along with copy of this table and the content transfer template and advise CT completed and advise they can send us additions or changes up to 5 days from the date of the email
Send Michael an email to set up walk-through and follow-up
After final email sent, send Carri and Shelly a copy of the CT template so they can invoice the client
After time elapsed, send SH, MT a note that content transfer is complete…Add all copies of excel template to the ticket and finish out this table and all notes
Close Ticket

## Content Transfer
Content Transfer for North Prairie Regional Water District
Old Site link & Content Transfer instructions | Transfer Items Checklist | New Site link & Item Checklist | Initial Item checklist | Final Item checklist
https://nprwd.com/ |  | https://nprwd.municipalimpact.com/
Municipal Impact will transfer content from the following pages/dropdowns ONLY: |  |  | 24 Pages of Content | 24 Pages of Content (10/15/24)
*Transfer of documents older than 2024 not included. |  |  | 69 PDFs | 52 PDFs (10/15/24)
*Client to provide 3rd Party Calendar link. |  |  | # | 17 PDFs needing OCR (10/15/24)
|  |  | 18 Images | 5 Images (10/22/24)
|  |  | 29 Links | 13 Links (10/22/24)
|  |  | 2 locations | 2 Locations (10/15/24)
|  |  | 30 Contacts | 16 Contacts (10/22/24)
|  |  | 6 News & Notices | 6 News & Notices (10/15/24)
|  |  | 2 Word docs | 2 Word docs (10/15/24)
|  |  | 1 video | 1 video (10/15/24)
Navigation Bar from Old Site | Notes to transfer from Old site to New site | Navigation Bar of New Site | Transfer Notes | Link to new site page
Home: |  | Home:
1 image - logo (water tower) | Transfer to logo section | Welcome to North Prairie! | Edited intro verbiage 10/22/24 | https://nprwd.municipalimpact.com/
1 image (water tower) | Transfer to Slideshow | Slide Show | Transferred 1 image & edited pixels 10/22/24 | https://nprwd.municipalimpact.com/
Promos: |  | Quicklinks: | Transferred verbiage to Contact Us quicklink & Renamed "Report Problem" to "Contact Us" | https://nprwd.municipalimpact.com/contact-us
Our Mission: verbiage & 1 link to other site page (About Us) | Create promo | Promos:
Bill Payment Options: verbiage & 1 link to other site page | Create promo | Conserve Water
How Well Do...: verbiage & 1 button/link to 1 PDF | Create promo | Our Mission | Created promo & transferred verbiage & 1 link 10/22/24
Whats in a drop...: 2 links to other site page & 1 image | Create promo | How Well Do You Know Your Water System? | Created promo & transferred 1 link/button 10/22/24
Customer Service: |  | Customers:
Contact Us |  | About Us | Transferred verbiage & 2 pdfs 10/22/24 | https://nprwd.municipalimpact.com/about-us
verbiage | transfer to contact us | Calendar of Events
1 contact us form | will not transfer/form on muni site | New Service/Transfer Request | Transferred verbiage 10/22/24 | https://nprwd.municipalimpact.com/new-service-transfer-request
New Service / Transfer Request |  | Water Rates & Policies | Transferred verbiage 10/22/24 | https://nprwd.municipalimpact.com/water-rates-and-policies
verbiage | Transfer to New Service/Transfer Request | Meter Reading | Transferred verbiage 10/22/24 | https://nprwd.municipalimpact.com/meter-reading
Rates & Policies |  | Payment Options | Transferred verbiage, 1 link, created 1 button 10/22/24 | https://nprwd.municipalimpact.com/payment-options
verbiage & 1 PDF | Transfer to Water Rates & Policies | Personnel | Transferred verbiage, 9 contacts, 2 tables 10/22/24 | https://nprwd.municipalimpact.com/personnel
Meter Reading |  | Locations & Directions | Transferred location, phone number, fax, office hours 10/22/24 | https://nprwd.municipalimpact.com/locations-and-directions
verbiage | Transfer to Meter Reading | Forms & Reports:
Bill Payment |  | New Service Forms
verbiage & 1 link | Transfer to Payment Options | Other Forms | Transferred 5 pdfs 10/22/24 | https://nprwd.municipalimpact.com/other-forms
About Us |  | Water Quality Report
verbiage & 2 word docs | Transfer to About Us | NP Bulk Water Filling Station | Transferred verbiage , 1 image, 3 pdfs 10/22/24 | https://nprwd.municipalimpact.com/np-bulk-water-filling-station
Personnel |  | Financial Reports/Audits | Transferred verbiage & 3 pdfs 10/22/24 | https://nprwd.municipalimpact.com/financial-reports-audits-1
verbiage | Transfer to Personnel | Governance:
Business Personnel: 3 contacts | Transfer to Personnel | Board Members | Transferred 7 contacts & verbiage 10/22/24 | https://nprwd.municipalimpact.com/board-members
Operations Personnel: 6 contacts | Transfer to Personnel | Board Meetings | Transferred verbiage 10/22/24 | https://nprwd.municipalimpact.com/board-meetings
Location |  | Agendas | Transferred 8 pdfs 10/22/24 | https://nprwd.municipalimpact.com/agendas
1 location & office hours & contact info | Transfer to Locations & Directions | Minutes | Transferred 23 pdfs 10/22/24 | https://nprwd.municipalimpact.com/minutes
Forms & Reports: |  | Resolutions
All Forms & Reports |  | Message From Your Chairperson | Transferred 1 pdf 10/21/24 | https://nprwd.municipalimpact.com/message-from-your-chairperson
2 PDFs | Transfer to Other Forms | News & Notices:
"NPRWD Mission..." 1 PDF needs OCR | Transfer to Other Forms | Recent News
1 PDF | Transfer to Other Forms | Alerts | transferred verbiage & 1 image 10/22/24 | https://nprwd.municipalimpact.com/alerts
"NP Crossing..." 1 PDF needs OCR | Transfer to Other Forms | Current Projects | transferred verbiage 10/21/24 | https://nprwd.municipalimpact.com/current-projects
Water Quality Report |  | Resources:
verbiage | Transfer to Water Quality Report | FAQ
4 PDFs need OCR | Transfer to Water Quality Report | Employment Opportunities | Transferred verbiage & 1 pdf 10/21/24 | https://nprwd.municipalimpact.com/employment-opportunities
8 PDFs | Transfer to Water Quality Report | Water Sense Scholarship
1 PDF needs OCR | Transfer to Water Quality Report | Conservation Tips
NP Bulk Water Filling Station |  | Whats in a Drop of Water? | Transferred 1 video 10/22/24 | https://nprwd.municipalimpact.com/what-s-in-a-drop-of-water
verbiage & 1 contact (link to email) | Transfer to NP Bulk Water Filling Station | How Well Do You Know Your Water System? | Transferred 2 pdfs 10/21/24 | https://nprwd.municipalimpact.com/how-well-do-you-know-your-water-system
1 image | Transfer to NP Bulk Water Filling Station | **Footer
3 PDFs | Transfer to NP Bulk Water Filling Station | Sites of Interest | Transferred 6 links (10/15/24)
Financials and or Audits |  | Facebook | Transferred 1 link (10/22/24)
verbiage & 1 contact | Transfer to Financial Reports/Audits
3 PDFs need OCR | Transfer to Financial Reports/Audits
News & Notices:
Recent News
5 Recent News items | Create RN items // do not transfer cents scholarship (only one announcing winners) //
"Resolutions Concerning..." 1 Recent News item & 3 PDFs need OCR | Create RN items
"North Prairie..." 1 Recent News item & 1 image | older than 2024 / not transferring
"Water Saving..." 1 Recent News item & 1 image | older than 2024 / not transferring
"Best of Minot..." 1 Recent News item & 1 contact & 1 link | older than 2024 / not transferring
"Water Cents..." 1 Recent News item & 2 links | older than 2024 / not transferring
ALERTS
verbiage & 1 image | Transfer to Alerts
Board Members | remove board qualifications
verbiage | Transfer to Board Members
5 PDFs linked | Transfer to Board Members
7 contacts | Transfer to Board Members
1 PDF (remaining are duplicates to line 80) | Transfer to Board Members
Board Meetings
verbiage | Transfer to Board Meetings
1 PDF | Transfer to Board Agendas
"NPRWD Board Special..." 1 PDF needs OCR | Transfer to Board Agendas
3 PDFs | Transfer to Board Agendas
Agendas-Minutes-Resolutions | (3 Agendas, 23 Minutes)
24 PDFs | Transfer to Agendas / Minutes pages
"February 16, 2023..." 1 PDF needs OCR | Transfer to Agendas / Minutes pages
"January 19, 2023..." 1 PDF needs OCR | Transfer to Agendas / Minutes pages
Current Projects
verbiage | Transfer to Current Projects
Whats in a drop of Water?
1 video (youtube) | Transfer to Whats in a drop of water?
How well do you know your water system?
1 PDF (duplicate to line 28) | Transfer to how well do you know your water system?
1 PDF | Transfer to how well do you know your water system?
Message from your Chairperson
1 PDF | Transfer to Message from your chairperson
Resources:
FAQ
*blank page* | nothing to transfer
Current Job Openings
verbiage | Transfer to Employment Opportunities
1 PDF needs OCR | Transfer to Employment Opportunities
New Page
*blank page*
**Footer
1 location, 1 contact info, 1 link to other site page | Transfer to Locations & Directions
Office hours | Transfer to Locations & Directions
Recent News: 5 links to other site pages | do not transfer links
Related links: 6 links (1 link already transferred) | Transfer to sites of interest// "Water Conservation Tips" link already transferred // ND State Water Commission link doesnt work for me 10/15/24
Facebook link: 1 link | Transfer to Footer
Color-Coded Legend
Planned, not completed
Page Tab
Subpage under Yellow tab
Do not transfer / Did not transfer

## Notes & Time Entries
Ticket | Site | Agent Assigned | Date | # of Hrs This Date | Total # of Hrs to Complete | Notes
**All time entry notes are in time entry section in ticket 12322
TOTAL: